YAARL 360 Home Services Platform Project Proposal & Development Plan Flutter • Django • Next.js • MySQL

| 4 Platforms | 3 Month Delivery | 2 Phases | Rs.10L Phase 1 Investment |
| --- | --- | --- | --- |

| Prepared for: YAARL 360 | Date: May 2026 | Version: v1.0 | Classification: Confidential |
| --- | --- | --- | --- |

# 1. Executive Summary

YAARL 360 is a hybrid home-services marketplace for Sri Lanka combining an on-demand emergency repair dispatch system (Uber-style) with a scheduled subscription maintenance service. This proposal delivers the platform in a structured two-phase approach, ensuring a fully functional, revenue-generating product is live within 3 months while leaving advanced features for a subsequent phase based on client confirmation.

Phase 1 (this proposal): Rs. 10,00,000 — Core platform with all essential booking, dispatch, worker, and subscription features delivered in 12 weeks. Phase 2 (optional next engagement): Advanced financial automation, multi-currency, SEO generator, and enterprise features — scoped and priced separately after Phase 1 launch.

This proposal covers four interconnected platforms:

- Customer App (iOS & Android) — Flutter

- Worker / Partner App (iOS & Android) — Flutter

- Core Marketing & Booking Website — Next.js (SSR)

- Super Admin Command Center — Next.js + Django REST

## 1.1  Phased Delivery Strategy

Rather than building everything at once and delivering a bloated product 4-5 months later, YAARL 360 is structured into two clearly defined phases. Phase 1 delivers a lean, complete, production-ready platform. Phase 2 enhances it based on real user feedback and client-confirmed priorities.

|  | Phase 1 (This Proposal) | Phase 2 (Future Engagement) |
| --- | --- | --- |
| Goal | Working product live in 3 months | Enhanced platform based on real usage |
| Timeline | 12 weeks (3 months) | 8–10 weeks post Phase 1 |
| Investment | Rs. 10,00,000 | Scoped after Phase 1 launch |
| Focus | Core booking, dispatch, subscriptions, admin | Payroll automation, SEO engine, multi-currency, B2B portal |
| Risk | Low — lean scope, clear deliverables | Informed by real user data from Phase 1 |

## 1.2  Business Model

| Revenue Stream | Description | Phase |
| --- | --- | --- |
| On-Demand Commissions | 20% platform fee on every gig job completed | Phase 1 |
| Subscription Plans | Monthly recurring Basic and Premium plans | Phase 1 |
| B2B Corporate Contracts | Custom SLA packages for hotels & offices | Phase 2 |
| Multi-Currency Billing | International diaspora subscriptions (LKR/USD/GBP) | Phase 2 |

# 2. Technology Stack

The platform uses proven, open-source technologies that run on the client-provided server without any mandatory cloud vendor lock-in.

| Layer | Technology | Why |
| --- | --- | --- |
| Mobile Apps | Flutter (Dart) | Single codebase compiles to native iOS & Android. Best performance among cross-platform frameworks. |
| Website | Next.js 14 (SSR) | Server-side rendering required for Google SEO ranking. Sub-1.5s load target. |
| Admin Panel | Next.js + Django REST | Shared UI components with website. Django provides structured API for admin operations. |
| Backend API | Django (Python) | Battle-tested, security-first. Celery for background tasks. DRF for clean REST API. |
| Database | MySQL | Reliable transactional database. Runs on client server. Spatial index for geo-radius queries. |
| Real-time | Django Channels + Redis | WebSocket job dispatch and live GPS broadcast without polling. |
| Push Notifications | Firebase Cloud Messaging | iOS & Android push — job alerts, booking confirmations, reminders. |
| GPS Tracking | Firebase Realtime DB | Live coordinate streaming between customer and technician. |
| File Storage | AWS S3 / Cloudflare R2 | Worker IDs, proof-of-work photos, invoice PDFs. |
| Payments | PayHere (LKR) + Stripe | PayHere for local LKR compliance. Stripe for card vaulting & subscription billing. |
| Maps | Google Maps Platform | Proximity matching, live tracking map, turn-by-turn navigation deep-links. |
| Deployment | Client-provided Linux server | Django + MySQL + Redis hosted on client infrastructure via Docker + Nginx. |
| CI/CD | GitHub Actions | Automated build, test, and deploy on every code push. |

CLIENT-PROVIDED (not included in this budget): Deployment server (Linux, min 4 vCPU / 8 GB RAM / 100 GB SSD), Apple Developer Account ($99/year), Google Play Developer Account ($25 one-time), PayHere merchant account, domain name, and SSL certificate. These must be ready by Week 8.

# 3. Phase 1 — Core Feature Specifications

Phase 1 delivers every feature needed to take real bookings, dispatch real workers, process real payments, and manage operations from day one. Features are deliberately scoped to the essential — no bloat, no half-built extras.

3.1 Customer App — iOS & Android (Flutter)

### 3.1.1  User Onboarding & Authentication

- Phone number registration with OTP verification (SMS via Dialog/Mobitel API).

- Profile setup: name, address, property type (apartment / house / commercial).

- City/area service-availability check before onboarding continues.

### 3.1.2  Dual Booking Flow

| On-Demand (Emergency) | Scheduled Booking |
| --- | --- |
| Uber-style live request to nearest worker | Calendar slot picker with date & time |
| 5–15 km auto-expanding broadcast radius | Service type and scope selector |
| Photo/video upload for issue description | Pre-arrival reminder push notification |
| Live GPS map: worker en-route | Reschedule up to 24 hours before visit |
| 30-second accept/reject countdown timer | Booking confirmation & worker profile view |
| Dynamic fare estimate before confirming | In-app chat with assigned worker |

### 3.1.3  Subscription Plans

| Feature | Basic | Premium / Villa |
| --- | --- | --- |
| Deep Cleaning | 1 bathroom or kitchen / month | Full property every 6 weeks |
| Handyman Checkups | 2 minor checkups / month | Unlimited, priority 24/7 |
| Visitation Fee | Standard rates | Waived on all on-demand |
| Response Priority | Standard queue | Top of dispatch queue |
| Billing | Monthly auto-renew (PayHere/Stripe) | Monthly or annual auto-renew |
| Visit Calendar | 12-month pre-schedule | 12-month editable pre-schedule |

- Secure card tokenization (PCI-DSS) — card stored once, billed automatically each cycle.

- Failed payment retry with 3-day grace period and in-app notification.

- Self-service pause and cancel with reason capture.

### 3.1.4  Supporting Features

- Booking history with job status tracking and PDF invoice download.

- In-app ratings and reviews after each completed job.

- Push notifications: job accepted, worker en-route, job complete, subscription renewal.

- Basic profile management: saved addresses, payment methods, notification preferences.

3.2 Worker / Partner App — iOS & Android (Flutter)

### 3.2.1  Mode A — Gig Worker (On-Demand)

| Feature | Specification |
| --- | --- |
| Online / Offline Toggle | Presence switch. Only online workers receive job broadcasts. |
| Job Radar | Live map: distance, estimated payout, service type, customer photo. |
| 30-Second Timer | Accept/reject countdown. Auto-routes to next worker on expiry. |
| Navigation | Google Maps deep-link for turn-by-turn directions to customer. |
| Job Completion | Photo proof upload + optional customer signature. Instant payout notification. |
| Earnings Screen | Daily and weekly earnings with commission breakdown (80% worker / 20% platform). |

### 3.2.2  Mode B — In-House Crew

| Feature | Specification |
| --- | --- |
| Shift Roster Viewer | Pre-assigned shifts, start/end times, team designations pushed from admin. |
| Daily Route Card | Property address, access notes, and contact for the day's visits. |
| GPS Check-In / Out | GPS-verified arrival and departure timestamps for hours logging. |
| Performance Score | Customer satisfaction and punctuality rating visible to worker. |

3.3 Core Website — Next.js 14 (SSR)

### 3.3.1  Phase 1 Website Features

- Homepage with city/ZIP service availability validator — checks coverage before showing booking options.

- Service overview pages — visual cards for each service category (cleaning, plumbing, electrical, AC, painting).

- Subscription pricing page — Basic vs Premium side-by-side with Subscribe Now checkout funnel.

- Gig worker sign-up page — multi-step form with NIC upload, skill selection, and certification upload.

- Booking initiation from web — redirects to app or handles web-based booking for non-app users.

- Contact and about pages. Google Analytics 4 event tracking on all key actions.

- Core Web Vitals optimised: LCP < 1.5s, mobile-first responsive design.

### 3.3.2  Phase 2 Website Additions

The following website feature is deferred to Phase 2 pending client confirmation:

Phase 2 Addition: Auto-generated geo SEO landing pages (/colombo/emergency-plumber, /jaffna/deep-cleaning) with JSON-LD schema markup and XML sitemap. Requires city and service content from the client across all combinations.

3.4 Super Admin Command Center — Next.js + Django REST

### 3.4.1  Phase 1 Admin Features

| Module | Phase 1 Capability |
| --- | --- |
| Live Dispatch Map | Full-screen Google Maps view: online workers (green), en-route (amber), on-site (blue). Real-time via WebSocket. |
| Matching Algorithm | Auto-assigns nearest online worker by distance + skill tag. Broadcast escalation 5km > 10km > 15km if no acceptance within 90 seconds. |
| Manual Override | Dispatcher drag-assigns any worker to any job with reason logging. |
| Job Management | View all active, pending, and completed jobs. Filter by city, service type, date. |
| Worker Management | Approve/reject worker applications. View profiles, ratings, and availability. |
| Customer Management | View customer accounts, booking history, subscription status. |
| Subscription Admin | View active subscribers, plan type, renewal date, manual cancel/upgrade. |
| Basic Revenue View | Total jobs completed, total subscription revenue, payout summary. |
| SLA Alerts | Premium jobs unassigned for more than 5 minutes trigger admin notification. |
| Content Management | Manage service categories, pricing, city coverage zones. |

### 3.4.2  Phase 2 Admin Additions

The following advanced admin features are deferred to Phase 2:

| Module | Phase 2 Capability |
| --- | --- |
| Automated Split Payroll | 80/20 commission auto-escrow via Celery tasks. Batch weekly payout processing to worker bank accounts with full audit trail. |
| In-House Payroll Engine | GPS check-in/out hours auto-fed into monthly salary calculator. Overtime auto-flagged. |
| MRR / Churn Dashboard | Monthly Recurring Revenue, churn rate, failed payment retry analytics, cancellation reason analysis. |
| Multi-Currency Billing | Toggle LKR / USD / GBP / AED per user country domain with live exchange rate sync. |
| B2B Enterprise Portal | Custom RFQ form, corporate account dashboard, multi-property billing, contract management. |
| Invoice Auto-Generation | Branded PDF invoices auto-generated for every job and subscription renewal via WeasyPrint. |

Phase 2 is not an afterthought — it is the advanced layer built on top of live production data from Phase 1. Starting Phase 2 after the client sees real bookings and subscriber numbers ensures these features are built for actual usage patterns, not assumptions.

# 4. Analytics & Reporting

Phase 1 ships with essential analytics to monitor platform health from day one. Advanced financial analytics are added in Phase 2.

| Metric | Description | Phase | Source |
| --- | --- | --- | --- |
| New customer registrations | By city and channel | 1 | MySQL |
| Booking funnel conversion | Step-by-step drop-off tracking | 1 | GA4 |
| On-demand vs scheduled split | Order type ratio | 1 | MySQL |
| Active subscription count | Basic vs Premium breakdown | 1 | Admin panel |
| Average job response time | Broadcast to acceptance | 1 | Django |
| Job fill rate | % of requests assigned | 1 | Django |
| Worker acceptance rate | Per-worker and overall | 1 | Django |
| Customer app store rating | iOS + Android combined | 1 | App stores |
| Website organic traffic | Sessions by city page | 1 | GA4 / Search Console |
| Platform uptime | Sentry + uptime monitor | 1 | Sentry |
| MRR / ARR | Monthly & annual recurring revenue | 2 | Finance engine |
| Churn rate & reasons | Subscription cancellation analytics | 2 | Finance engine |
| Worker earnings analytics | Per-worker payout and performance | 2 | Payroll engine |

# 5. Development Timeline — 12-Week Sprint Plan

Phase 1 is delivered across 12 weeks with parallel development tracks for mobile, backend, and web. Phases overlap where dependencies allow to maximise delivery speed.

| Phase | Weeks | Deliverables |
| --- | --- | --- |
| Foundation | 1 – 3 | Django API scaffold, MySQL schema (users, workers, bookings, subscriptions, jobs), JWT + OTP authentication, role-based access control, PayHere & Stripe integration, Firebase project setup, GitHub Actions CI/CD, staging environment on development server. |
| Mobile — Customer App | 4 – 7 | Flutter Customer App: onboarding, on-demand booking flow, scheduled booking, live GPS tracking screen, subscription purchase + PayHere checkout, booking history, push notifications, ratings & reviews. |
| Mobile — Worker App | 5 – 8 | Flutter Worker App: online/offline toggle, job radar screen, 30-second accept/reject timer, navigation deep-link, proof-of-work photo upload, earnings screen, in-house shift roster, GPS check-in/check-out. (Runs parallel with Customer App tail.) |
| Website | 7 – 10 | Next.js 14 website: homepage with city validator, service pages, subscription pricing + checkout, gig worker sign-up funnel, GA4 tracking, Core Web Vitals optimisation. |
| Admin Center | 8 – 11 | Admin command center: live dispatch map, matching algorithm, manual override, job management, worker management, subscription admin, basic revenue view, SLA alert system. |
| QA & Launch | 11 – 12 | End-to-end integration testing across all 4 platforms, UAT with client, Flutter builds submitted to App Store and Google Play (via client accounts), production deployment on client server, DNS + SSL, Sentry monitoring setup, handover documentation. |

## 5.1  Weekly Sprint Detail

| Week | Sprint Deliverables |
| --- | --- |
| Wk 1 | MySQL database schema design: users, workers, bookings, subscriptions, jobs, service categories. Django project setup, environment configuration, GitHub repository and Actions CI/CD. |
| Wk 2 | Django authentication: JWT tokens, OTP via SMS (Dialog API), user role guards (customer / worker / admin). PayHere merchant integration, card tokenization, webhook handling. Stripe subscription billing setup. |
| Wk 3 | Booking API: on-demand request lifecycle state machine (pending to broadcast to accepted to en-route to completed). Django Channels WebSocket server for live dispatch. Firebase Cloud Messaging integration. |
| Wk 4 | Flutter Customer App: onboarding screens, home screen, city validator, on-demand booking flow, map screen with live worker markers. |
| Wk 5 | Flutter Customer App: scheduled booking calendar, subscription purchase screens, PayHere checkout integration, Django Celery auto-renew scheduler. Flutter Worker App: online/offline toggle, job radar map. |
| Wk 6 | Flutter Customer App: live GPS tracking screen (Firebase), in-app chat (Firebase Realtime DB), rating and review flow. Flutter Worker App: 30-second accept/reject timer, navigation deep-link. |
| Wk 7 | Flutter Customer App: booking history, push notification preferences. Flutter Worker App: earnings screen, proof-of-work photo upload, earnings summary. |
| Wk 8 | Flutter Worker App: in-house shift roster, GPS check-in/check-out, performance score view. Next.js website: homepage, service pages, city validator component. |
| Wk 9 | Next.js website: subscription pricing + checkout funnel, gig worker sign-up form with file uploads to S3, GA4 event tracking. |
| Wk 10 | Admin command center: live dispatch map (Google Maps + WebSocket), job management tables, worker approval workflow, subscription admin panel. |
| Wk 11 | Admin: matching algorithm tuning, manual override, SLA alerts, basic revenue summary. Full end-to-end integration testing across all platforms. Performance optimisation. |
| Wk 12 | Client UAT and final bug fixes. Flutter builds prepared for App Store and Google Play (via client accounts). Production deployment on client server (Docker + Nginx + Gunicorn). DNS, SSL, Sentry monitoring. Handover documentation and admin training session. |

# 6. Investment & Cost Breakdown — Phase 1

All figures are in Sri Lankan Rupees (LKR). This covers the complete Phase 1 scope including design, development, integration, QA, and one month of post-launch support.

NOT INCLUDED IN THIS BUDGET — Third-party service costs (Google Maps API, Firebase, AWS S3/Cloudflare R2, SendGrid email, SMS OTP via Dialog/Mobitel, PayHere transaction fees, Stripe processing fees, Sentry monitoring) are usage-based and billed directly to the client by each service provider. These are operational costs that vary with platform usage — not development costs. Additionally: Deployment server hardware, Apple Developer Account ($99/year), Google Play Developer Account ($25 one-time), PayHere merchant account, domain name, and SSL certificate are client-provided and not included.

## 6.1  Development

| Deliverable | Duration | Cost (LKR) |
| --- | --- | --- |
| Django Backend API — all booking, dispatch, subscription, and auth endpoints | Wk 1–12 | Rs. 1,50,000 |
| MySQL Database Schema & Migrations | Wk 1–2 | Rs. 10,000 |
| Flutter Customer App — iOS & Android | Wk 4–9 | Rs. 1,60,000 |
| Flutter Worker App — iOS & Android (dual mode) | Wk 5–9 | Rs. 1,20,000 |
| Next.js 14 Website with SSR | Wk 8–11 | Rs. 1,00,000 |
| Admin Command Center (Next.js + Django REST) | Wk 10–11 | Rs. 1,10,000 |
| Payment Integration — PayHere + Stripe + auto-renew | Wk 2–5 | Rs. 28,000 |
| Real-time Dispatch Engine + Matching Algorithm | Wk 10–11 | Rs. 38,000 |
| Firebase — GPS tracking + FCM push notifications | Wk 6–7 | Rs. 20,000 |
| CI/CD Pipeline + GitHub Actions + Docker setup | Wk 1 | Rs. 14,000 |
| Development Subtotal |  | Rs. 7,50,000 |

## 6.2  UI/UX Design

| Item | Cost (LKR) |
| --- | --- |
| Figma UI/UX design — Customer App, Worker App, Website, Admin Panel (full design system + component library) | Rs. 55,000 |
| App icons, splash screens, and App Store / Google Play listing graphic assets | Rs. 12,000 |
| Brand color palette, typography, and design token integration across all platforms | Rs. 8,000 |
| Design Subtotal | Rs. 75,000 |

## 6.3  Quality Assurance

| Item | Cost (LKR) |
| --- | --- |
| Functional QA — manual testing of all user flows across Customer App, Worker App, Website, and Admin | Rs. 35,000 |
| API load testing — 200 concurrent users on booking and dispatch endpoints | Rs. 10,000 |
| Security review — OWASP Top 10 check on auth, payment, and file upload flows | Rs. 20,000 |
| Device compatibility testing — 5 iOS + 5 Android device configurations | Rs. 10,000 |
| QA Subtotal | Rs. 75,000 |

## 6.4  Post-Launch Support — 1 Month

| Item | Cost (LKR) |
| --- | --- |
| Critical and high-priority bug fixes with 24-hour response SLA | Rs. 25,000 |
| Uptime and error monitoring with alert response (Sentry) | Rs. 10,000 |
| Admin panel training session and full handover documentation | Rs. 15,000 |
| Support Subtotal | Rs. 50,000 |

## 6.5  Full Phase 1 Investment Summary

| Category | Amount (LKR) |
| --- | --- |
| Development (Django, Flutter apps, Next.js website, Admin) | Rs. 7,50,000 |
| UI/UX Design (Figma, design system, store assets) | Rs. 75,000 |
| Quality Assurance & Testing | Rs. 75,000 |
| Post-Launch Support (1 month) | Rs. 50,000 |
| Subtotal | Rs. 9,50,000 |
| Contingency Reserve (5%) | Rs. 50,000 |
| TOTAL PHASE 1 INVESTMENT | Rs. 10,00,000 |
| FIXED PRICE — No hidden extras | Rs. 10,00,000 LKR |

This is a fixed-price engagement. The Rs. 10,00,000 total covers everything listed in this document. No additional charges will be raised unless the client requests features outside the defined scope.

# 7. Payment Milestones

Five milestone payments tied to demonstrable deliverables. Each payment is released only when the corresponding deliverable is reviewed and approved by the client.

| # | Milestone | Deliverable Criteria | Payment |
| --- | --- | --- | --- |
| M1 | Kickoff | Signed contract, requirements confirmed, Figma design system delivered, staging environment set up, GitHub repository created. | Rs. 2,00,000 (20%) |
| M2 | Backend + Auth | Django API live on staging, MySQL schema complete, JWT+OTP auth working, PayHere + Stripe integrated and tested in sandbox. | Rs. 2,50,000 (25%) |
| M3 | Both Mobile Apps | Flutter Customer App and Worker App both demonstrable on TestFlight (iOS) and Play Console internal track (Android) with all core flows working. | Rs. 2,00,000 (20%) |
| M4 | Website + Admin | Next.js website live on staging. Admin command center operational with dispatch map, job management, and subscription admin. | Rs. 2,00,000 (20%) |
| M5 | Go-Live | Production deployment on client server, App Store and Google Play submissions via client accounts, UAT passed, documentation delivered. | Rs. 1,50,000 (15%) |
|  | Rs. 10,00,000 |  | Rs. 10,00,000 |

# 8. Client Responsibilities

The following must be provided by the client. These are not part of the development budget. Delays in provisioning these items will directly impact delivery dates.

| Item | Details | Required By |
| --- | --- | --- |
| Deployment Server | Linux VPS or dedicated server — minimum 4 vCPU, 8 GB RAM, 100 GB SSD, Ubuntu 22.04. SSH access provided to the development team. | Week 8 |
| Apple Developer Account | Active Apple Developer Program membership ($99/year). Required to submit Flutter iOS build to App Store. Registered under client entity. | Week 10 |
| Google Play Developer Account | Active Google Play Console account ($25 one-time). Required to upload Flutter Android build. Registered under client entity. | Week 10 |
| PayHere Merchant Account | Client registers at PayHere.lk and completes merchant onboarding. Live API credentials shared with development team. | Week 2 |
| Domain Name | Production domain (e.g., yaarl360.com). DNS management access needed during go-live in Week 12. | Week 11 |
| SSL Certificate | Free via Let's Encrypt (configured by team) or commercial cert if preferred (client procures). | Week 12 |
| Brand Assets | Final approved logo (SVG/AI), color palette, and typography guide within 5 business days of kickoff. | Week 1 |
| Subscription Pricing | Final LKR prices for Basic and Premium plans confirmed before payment integration begins. | Week 2 |
| UAT Feedback | One nominated point of contact for approvals. Feedback on each milestone within 3 business days. | Ongoing |

App Store and Google Play review timelines (typically 1–7 days) are controlled by Apple and Google, not the development team. Milestone 5 payment is not held pending App Store or Google review approval.

# 9. Phase 2 — Advanced Features (Post-Launch)

Phase 2 is a separate engagement scoped and priced after Phase 1 launches. The exact features and order of priority will be decided based on real usage data from the live platform. Estimated timeline: 8–10 weeks.

| Feature Area | Description |
| --- | --- |
| Automated Payroll Engine | 80/20 commission auto-escrow via Celery. Batch weekly payout to worker bank accounts with full audit trail and transaction references. |
| In-House Salary System | GPS check-in/out hours auto-fed into monthly salary calculator. Overtime auto-flagged and approved by admin. |
| MRR & Churn Analytics | Monthly Recurring Revenue dashboard, churn rate tracking, failed payment retry management, cancellation reason analysis. |
| Multi-Currency Billing | Toggle LKR / USD / GBP / AED per user country domain with live exchange rate sync for diaspora customers. |
| B2B Enterprise Portal | Corporate client account management, custom RFQ form, multi-property billing, contract upload and digital signature. |
| Invoice Auto-Generation | Branded PDF invoices auto-generated for every completed job and subscription renewal. |
| Geo SEO Landing Pages | Auto-generated /[city]/[service] pages (e.g. /colombo/emergency-plumber) with schema markup, XML sitemap, unique local content. |
| Worker Loyalty & Leaderboard | Top performer leaderboard, bonus tracking, earnings milestone rewards. |
| Advanced Admin Analytics | Worker utilisation rates, zone coverage gaps, demand heatmaps by city and time-of-day. |

Phase 2 investment will be separately quoted based on confirmed feature priorities after Phase 1 go-live. Estimated range: Rs. 4,00,000 – Rs. 6,00,000 depending on scope selected.

# 10. Risk Management

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| App Store review rejection | Medium | High | Build to Apple Human Interface Guidelines from day one. Submit 2 weeks before target go-live. Client account must be in good standing. |
| PayHere merchant onboarding delay | Medium | High | Client initiates registration at kickoff. Stripe sandbox used for payment testing in parallel throughout development. |
| Client server not ready on time | Medium | High | Development runs on a staging server throughout. Client server delay shifts go-live proportionally but does not affect development milestones. |
| Dispatch engine complexity | Low | Medium | 3-sprint dedicated focus on matching algorithm. Benchmark target: sub-2 second assignment at 100 concurrent requests. |
| GPS accuracy on budget Android devices | Low | Medium | Flutter app tested specifically on Redmi and Samsung A-series. Location smoothing algorithm implemented. |
| Scope creep requests | Medium | Medium | Any new feature outside Phase 1 scope is logged, estimated, and deferred to Phase 2. Phase 1 price is fixed. |

# 11. Go-Live Success Metrics — 90 Days

| KPI | 30-Day Target | 90-Day Target |
| --- | --- | --- |
| Customer app downloads (iOS + Android) | 500+ | 2,000+ |
| Registered gig workers onboarded | 50+ | 200+ |
| Completed on-demand jobs | 100+ | 500+ |
| Active subscription plans | 25+ | 150+ |
| Average job response time | < 8 minutes | < 5 minutes |
| App store rating (iOS + Android) | ≥ 4.0 stars | ≥ 4.3 stars |
| Website organic sessions / month | 500+ | 2,500+ |
| Platform uptime | > 99% | > 99.5% |
| Worker app acceptance rate | > 75% | > 85% |

# 12. Assumptions & Exclusions

## 12.1  Assumptions

- Client provides all brand assets (logo SVG/AI, color palette, typography guide) within 5 business days of kickoff.

- Subscription plan pricing in LKR is confirmed by the client before Week 2.

- One nominated client contact handles all approvals with a 3-business-day maximum response SLA.

- PayHere merchant account registration is initiated by the client at the same time as project kickoff — this cannot be delayed.

- Content for the website (service descriptions, city coverage, about page text) is provided by the client in English.

## 12.2  Exclusions — Not in Phase 1 Scope

| Excluded | Notes |
| --- | --- |
| Deployment server, hosting, and server costs | Client responsibility — see Section 8 |
| Apple Developer Account ($99/year) | Client responsibility — see Section 8 |
| Google Play Developer Account ($25) | Client responsibility — see Section 8 |
| Third-party API usage costs (Maps, Firebase, SMS, email, S3, Sentry) | Usage-based — billed directly to client by each provider based on actual platform usage |
| Automated payroll split and batch payouts | Phase 2 — see Section 9 |
| MRR / churn / advanced financial dashboards | Phase 2 — see Section 9 |
| Multi-currency billing (USD / GBP / AED) | Phase 2 — see Section 9 |
| Auto-generated geo SEO landing pages | Phase 2 — see Section 9 |
| B2B enterprise portal and corporate invoicing | Phase 2 — see Section 9 |
| Invoice PDF auto-generation | Phase 2 — see Section 9 |
| Multilingual support (Tamil / Sinhala) | English-first for Phase 1 launch |

# 13. Next Steps

To proceed with the YAARL 360 Phase 1 engagement:

- Proposal review and scope confirmation — client confirms Phase 1 feature scope within 5 business days.

- Contract signing — development agreement executed with the milestone payment schedule formalised.

- Milestone 1 payment — Rs. 2,20,000 (20%) to initiate the project and begin design sprint.

- Brand assets delivery — logo, color palette, and typography guide within 5 business days of kickoff.

- PayHere merchant account registration — initiated by client in parallel with Week 1 (this is on the critical path for Milestone 2).

- Kickoff meeting — 2-hour session to align on city coverage list, service categories, subscription pricing, and worker skill taxonomy.

- Sprint 1 begins — MySQL schema design and Django project scaffolding.

This proposal is valid for 30 days from the date of issue. YAARL 360 — Building Sri Lanka's Home Services Future