YAARL 360

Home Services Platform

Project Proposal

Flutter  •  Django  •  Next.js  •  MySQL

| 4 Platforms | 3 Months Delivery | 2 Phases | Rs. 10L Total Budget |
| --- | --- | --- | --- |

| Client: YAARL 360 (Pvt) Ltd | Date: May 2026 | Version: v1.0 |
| --- | --- | --- |

1.  Overview

YAARL 360 is a home services platform for Sri Lanka that connects homeowners with skilled workers for on-demand repairs and scheduled maintenance. The platform combines live job dispatch, subscription plans, and a full admin dashboard — delivered across four connected products.

| Platform | Description |
| --- | --- |
| Customer App | iOS & Android app for booking, tracking, and subscription management |
| Worker App | iOS & Android app for receiving jobs, GPS tracking, and earnings |
| Website | Marketing and booking website with service pages and subscription checkout |
| Admin Panel | Command center for managing jobs, workers, payments, and reports |

2.  What We Will Build

Customer App

Customers can book emergency on-demand services or schedule regular maintenance visits. They can track the worker live on a map, pay through the app, subscribe to monthly maintenance plans, and view their booking history.

Worker App

Workers receive job requests on their phone, accept or reject within 30 seconds, and navigate to the customer. Earnings, job history, and GPS check-in/out are all tracked in the app. Supports both gig workers and in-house staff.

Website

A clean marketing and booking website covering service pages, subscription plan comparison, and a sign-up form for new workers. Built for fast loading and mobile-friendly browsing.

Admin Panel

A live operations dashboard for the YAARL 360 team — monitor active jobs on a map, assign workers manually, manage subscriptions, approve worker applications, and view revenue summaries.

3.  Technology

| Layer | Technology |
| --- | --- |
| Mobile Apps (Customer + Worker) | Flutter — single codebase for iOS & Android |
| Website & Admin Panel | Next.js (React) — fast, SEO-ready |
| Backend API | Django (Python) — secure and reliable |
| Database | MySQL — standard relational database |
| Real-time Dispatch | Django Channels + Redis — live job broadcasts |
| Live GPS Tracking | Firebase Realtime Database |
| Push Notifications | Firebase Cloud Messaging |
| Payments | PayHere (LKR local) + Stripe (card billing) |
| File Storage | AWS S3 / Cloudflare R2 |
| Hosting | Client-provided Linux server (Docker + Nginx) |

4.  Delivery Timeline — 12 Weeks

| Phase | Weeks | What Gets Delivered |
| --- | --- | --- |
| Foundation | 1 – 3 | Backend API, database, authentication, payment integration, server setup |
| Customer App | 4 – 7 | Full Flutter customer app — booking, live tracking, subscriptions, payments |
| Worker App | 5 – 8 | Full Flutter worker app — job dispatch, GPS, earnings, shift management |
| Website | 7 – 10 | Next.js website — service pages, subscription checkout, worker sign-up |
| Admin Panel | 8 – 11 | Admin dashboard — live dispatch map, job management, worker and subscription admin |
| Testing & Launch | 11 – 12 | Full testing, client review, App Store + Google Play submission, go-live |

5.  Investment Breakdown

5.1  Development

| Deliverable | Cost (LKR) |
| --- | --- |
| Django Backend API — booking, dispatch, subscriptions, auth | Rs. 1,50,000 |
| MySQL Database Schema & Setup | Rs. 10,000 |
| Flutter Customer App — iOS & Android | Rs. 1,60,000 |
| Flutter Worker App — iOS & Android | Rs. 1,20,000 |
| Next.js Website | Rs. 1,00,000 |
| Admin Command Center | Rs. 1,10,000 |
| Payment Integration — PayHere + Stripe | Rs. 28,000 |
| Live Dispatch Engine | Rs. 38,000 |
| Firebase — GPS Tracking + Push Notifications | Rs. 20,000 |
| CI/CD Pipeline + Server Setup | Rs. 14,000 |
| Development Subtotal | Rs. 7,50,000 |

5.2  Design & UX

| Item | Cost (LKR) |
| --- | --- |
| UI/UX Design — Customer App, Worker App, Website, Admin (Figma) | Rs. 55,000 |
| App Icons, Splash Screens, App Store Listing Assets | Rs. 12,000 |
| Brand Integration — Colors, Typography | Rs. 8,000 |
| Design Subtotal | Rs. 75,000 |

5.3  Quality Assurance

| Item | Cost (LKR) |
| --- | --- |
| Manual Testing — All platforms and user flows | Rs. 35,000 |
| Load Testing — Booking and dispatch endpoints | Rs. 10,000 |
| Security Review — Payments and authentication | Rs. 20,000 |
| Device Testing — iOS & Android devices | Rs. 10,000 |
| QA Subtotal | Rs. 75,000 |

5.4  Post-Launch Support — 1 Month

| Item | Cost (LKR) |
| --- | --- |
| Bug Fixes — Critical issues within 24-hour response | Rs. 25,000 |
| Uptime Monitoring & Alert Response | Rs. 10,000 |
| Admin Training & Handover Documentation | Rs. 15,000 |
| Support Subtotal | Rs. 50,000 |

5.5  Total Investment Summary

| Category | Amount (LKR) |
| --- | --- |
| Development | Rs. 7,50,000 |
| Design & UX | Rs. 75,000 |
| Quality Assurance | Rs. 75,000 |
| Post-Launch Support | Rs. 50,000 |
| Subtotal | Rs. 9,50,000 |
| Contingency Reserve (5%) | Rs. 50,000 |
| TOTAL INVESTMENT | Rs. 10,00,000 |

Note: Third-party service costs (Google Maps, Firebase, SMS OTP, SendGrid, AWS S3, PayHere transaction fees, Stripe processing fees) are usage-based and billed directly to the client by each provider. These are not included in the above budget.

6.  Payment Milestones

Payment is tied to deliverables. Each milestone is paid only after the client reviews and approves the delivery.

| # | Milestone | Deliverable | Payment |
| --- | --- | --- | --- |
| M1 | Kickoff | Signed contract, Figma designs, staging environment ready | Rs. 2,00,000 (20%) |
| M2 | Backend + Auth | API live, database complete, payments integrated and tested | Rs. 2,50,000 (25%) |
| M3 | Mobile Apps | Customer App + Worker App on TestFlight and Play Console | Rs. 2,00,000 (20%) |
| M4 | Website + Admin | Website live on staging, Admin panel operational with dispatch | Rs. 2,00,000 (20%) |
| M5 | Go-Live | Production deployment, App Store + Play Store submitted, handover done | Rs. 1,50,000 (15%) |
|  | TOTAL |  | Rs. 10,00,000 |

7.  Client Responsibilities

The following items are not included in the budget and must be provided by the client:

| Item | Required By |
| --- | --- |
| Linux server (min 4 vCPU / 8 GB RAM / 100 GB SSD) | Week 8 |
| Apple Developer Account ($99/year) | Week 10 |
| Google Play Developer Account ($25 one-time) | Week 10 |
| PayHere merchant account (free to register) | Week 2 |
| Domain name and SSL certificate | Week 11 |
| Brand assets — logo, colors, typography guide | Week 1 |

8.  Phase 2 — Future Enhancements

Phase 2 is a separate engagement after Phase 1 launches. Features will be prioritised based on real usage data. Estimated cost: Rs. 4,00,000 – Rs. 6,00,000.

| Feature | Description |
| --- | --- |
| Automated Payroll | 80/20 commission split with batch weekly payouts to workers |
| MRR & Analytics Dashboard | Monthly revenue, churn, and subscription analytics |
| Multi-Currency Billing | LKR / USD / GBP / AED support for diaspora customers |
| B2B Enterprise Portal | Corporate accounts, custom contracts, multi-property billing |
| Geo SEO Landing Pages | Auto-generated city/service pages for Google ranking |
| Invoice Auto-Generation | Branded PDF invoices for every job and subscription renewal |

9.  Next Steps

Review and confirm proposal scope within 5 business days

Sign development agreement with milestone payment schedule

First payment — Rs. 2,00,000 (20%) to initiate project and begin design

Deliver brand assets within 5 business days of kickoff

Register PayHere merchant account (must be ready by Week 2)

Kickoff meeting — align on city coverage, service categories, pricing

This proposal is valid for 30 days from the date of issue.

YAARL 360 — Building Sri Lanka's Home Services Future